## Gantt Chart
Task ID | Task Description | Duration | Start | End | Status
1 | Concept and Planning | 2 | 2022-08-01 | 2022-08-02 | 50% | 1
1.1 | Evaluate Project Instruction and Guidelines | 2 | 2022-08-03 | 2022-08-04 | 25% | 0.5
1.2 | Develop Project Plan | 2 | 2022-08-06 | 2022-08-07 | 100% | 2
1.2.1 | Define Project Background | 2 | 2022-08-08 | 2022-08-09 | 35% | 0.7
1.2.2 | Define Project Scope | 2 | 2022-08-10 | 2022-08-11 | 20% | 0.4
1.2.3 | Define Work Breakdown Structure | 3 | 2022-08-12 | 2022-08-14 | 85% | 2.55
1.2.4 | Activity Definition and Estimation | 2 | 2022-08-15 | 2022-08-16 | 85% | 1.7
1.2.5 | Develop Gantt Chart | 3 | 2022-08-17 | 2022-08-19 | 50% | 1.5
1.3 | Divide Member’s Task | 1 | 2022-08-20 | 2022-08-20 | 60% | 0.6
2 | Software Design | 3 | 2022-08-21 | 2022-08-23 | 75% | 2.25
2.1 | Develop System Vision | 2 | 2022-08-24 | 2022-08-25 | 100% | 2
2.2 | Define Requirement | 2 | 2022-08-26 | 2022-08-27 | 60% | 1.2
2.2.1 | Define User Requirements | 2 | 2022-08-28 | 2022-08-29 | 40% | 0.8
2.2.2 | Define Software Requirements | 2 | 2022-08-30 | 2022-08-31 | 50% | 1
2.3 | Develop Use Case | 5 | 2022-09-01 | 2022-09-05 | 30% | 1.5
2.4 | Define System Components | 3 | 2022-09-06 | 2022-09-08 | 20% | 0.6
2.5 | Design User Interface | 2 | 2022-09-09 | 2022-09-10 | 30% | 0.6
2.6 | Project Part A Submission | 1 | 2022-09-11 | 2022-09-11 | 100% | 1
3 | Software Implement | 7 | 2022-09-12 | 2022-09-18 | 0% | 0
4 | Software Testing | 7 | 2022-09-19 | 2022-09-25 | 0% | 0
4.1 | Unit Testing | 7 | 2022-09-26 | 2022-10-02 | 0% | 0
4.2 | Requirement Acceptance Testing | 4 | 2022-10-03 | 2022-10-06 | 0% | 0
5 | Software Development | 7 | 2022-10-07 | 2022-10-13 | 0% | 0
6 | Final Project Submission | 1 | 2022-10-14 | 2022-10-14 | 0% | 0
6
Formulas:
End = [Start]+[Duration]-1

## Project Planner
Project Title
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Activity 01 | 1 | 5 |  |  | 0%
Activity 02 |  |  |  |  | 0%
Activity 03 |  |  |  |  | 0%
Activity 04 |  |  |  |  | 0%
Activity 05 |  |  |  |  | 0%
Activity 06 |  |  |  |  | 0%
Activity 07 |  |  |  |  | 0%
Activity 08 |  |  |  |  | 0%
Activity 09 |  |  |  |  | 0%
Activity 10 |  |  |  |  | 0%
Activity 11 |  |  |  |  | 0%
Activity 12 |  |  |  |  | 0%
Activity 13 |  |  |  |  | 0%
Activity 14 |  |  |  |  | 0%
Activity 15 |  |  |  |  | 0%
Activity 16 |  |  |  |  | 0%
Activity 17 |  |  |  |  | 0%
Activity 18 |  |  |  |  | 0%
Activity 19 |  |  |  |  | 0%
Activity 20 |  |  |  |  | 0%
Activity 21 |  |  |  |  | 0%
Activity 22 |  |  |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 0%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%
Activity 27 |  |  |  |  | 0%
Activity 28 |  |  |  |  | 0%
Activity 29 |  |  |  |  | 0%
Activity 30 |  |  |  |  | 0%
Activity 31 |  |  |  |  | 0%
Activity 32 |  |  |  |  | 0%
Activity 33 |  |  |  |  | 0%
Activity 34 |  |  |  |  | 0%
Activity 35 |  |  |  |  | 0%